Risk Assessment and Management Guide

Completing a risk assessment creates a Risk Management Plan and is an essential process that must be completed for Council to be satisfied that your project or event will be delivered in a safe manner with potential risks having been considered and controlled in some manner.

Council Officers have created the following risk assessment template to support you in identifying and documenting risks related to your project. The document includes:

- Steps to complete a risk assessment and complete a Risk Management Plan

- A completed Risk Management Plan example on page 5

- A Risk Management Template on page 9.

We recommend that you complete the Risk Management Plan template in detail, distribute to all relevant members of your project team/organisation and obtain their feedback prior to finalising.

To complete the Risk Management Plan template, you will need to:

Step1: Identify who your project or event Risk Management Officer is, i.e. who will have overall responsibility for preparation and implementation of your Risk Management Plan.

Step 2: List who is involved in compiling the Risk Management Plan and the date.

Step 3: In column 1 - List all the steps/processes or contributors involved in your project that may present   hazards

Step 4: In column 2 – List any hazard(s) & the risk(s) caused by the activity listed in column 1. Note: hazards can present risk to people, the environment, buildings or equipment. It is important to try and capture all risks. Consider anything that can cause harm or damage

Now you need to consider the likelihood of each of your risks occurring and the consequences should it occur.

Step 5: In column 3 – use Table 2. Qualitative Measures of Consequence on page 3 to determine the level of consequence for each of the risks should they occur and record in column 3. This will range from A to E with A being Catastrophic through to E being Insignificant.

Step 6: In column 4 - use Table 3. Qualitative Measures of Likelihood on page 3 to determine the likelihood of each of the risks happening and record in column 4. This will range from 1 to 5 with 1 being almost certain through to 5 being rare.

Step 7: In column 5 - Once you have the two ratings for each of your risks you can identify the overall risk rating by using Table 1. Risk Assessment Matrix. Record the risk rating in Column 5. The rating will either be E for Extreme, H for High, M for Medium or L for low.

Step 8: In column 6 - Now that you have your risk rating for each of the risks identified, you will need to consider what control(s) you can put in place to eliminate or minimise the risk occurring. Document your controls in Column 6

Step 9: In Column 7 – Repeat steps 5, 6 and 7 to rate the risk again to see how the control you have identified has improved the situation. You should see a reduction in the likelihood and/or the consequence and therefore have a lower risk rating overall

Step 10: In Column 8 – Nominate the person(s) responsible for putting the control in place.

Step 11: In Column 9 – Nominate the date the control will be in place.

Step 12: In Column 10 – Note when the control was put in place. Your Risk Management Plan is a living document and should be used to monitor effective risk management throughout the lifecycle of your project.

Step 13: Ensure the Risk Management Plan is communicated to all stakeholders.

Note: Certain stakeholders such as performers, drone operators or amusement ride operators must provide a separate Risk Management Plan specific to their activity if the risk rating is greater than Low. These people will/should know the risks associated with their activity better than you. You must be confident their risks are controlled properly.

Table 1. Risk Assessment Matrix

| ## Consequence | ### Likelihood |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | (1) Almost Certain | (2) Likely | (3) Possible | (4) Unlikely | (5) Rare |
| (A) Catastrophic | E | E | E | H | H |
| (B) Major | E | H | H | H | M |
| (C) Moderate | H | M | M | M | L |
| (D) Minor | M | M | L | L | L |
| (E) Insignificant | L | L | L | L | L |
| E = extreme risk; immediate action required. If personal injury is imminent, do not proceed. |  |  |  |  |  |
| H = high risk; senior management attention needed |  |  |  |  |  |
| M = medium risk; management responsibility must be specified |  |  |  |  |  |
| L = low risk; manage by routine procedures |  |  |  |  |  |

Table 2. Qualitative Measures of Consequence

| Level | Descriptor | Example detail description |
| --- | --- | --- |
| A | Catastrophic | Death; >$500K loss; toxic release off-site with huge detrimental effect; widespread irreparable loss of habitat; serious national media outcry. |
| B | Major | Extensive injuries; $50K - $500K loss; loss of production capability; off-site toxic release with significant detrimental effects; significant irreparable loss of habitat; serious public or local media outcry. |
| C | Moderate | Medical treatment required; $10K - $50K loss; on-site toxic release contained with outside assistance; considerable irreparable loss of habitat; high financial loss; significant adverse media. |
| D | Minor | First aid treatment; $1K - $10K loss; on-site toxic release immediately contained; minor loss of habitat; attention from media; concern by community. |
| E | Insignificant | No injuries; low financial loss; no community concern. |

Table 3. Qualitative Measures of Likelihood

| Level | Descriptor | Description |
| --- | --- | --- |
| 1 | Almost certain | - Is expected to occur in most circumstances, or - Risk is occurring now, or - Could occur within “days to weeks” |
| 2 | Likely | - Will probably occur in most circumstances, or - Could occur within “weeks to months” |
| 3 | Possible | - Might occur at some time, or - Could occur within “months to years” |
| 4 | Unlikely | - Could occur at some time, or - May occur but not anticipated, or - Could occur in “years to decades” |
| 5 | Rare | - May only occur in exceptional circumstances, or - Only occur as a “100 year event” |

| HIGH risk: 15 - 25 | - Issue represents a control weakness, which could cause or is causing major disruption of the process or major adverse effect on the ability of the process to achieve its objectives. Requires significant senior management intervention and should be reported to Executive Team Leadership immediately. Potential for resource diversion and may require possible external assistance. Requires high priority to be actioned within 0 – 3 months. |
| --- | --- |
| MEDIUM risk: 5 - 12 | - Issue represents a control weakness, which could cause or is causing moderate adverse effect on the ability of the process to achieve its objectives. Requires prompt escalation to responsible Management Group as may require possible external assistance. Requires prompt action. Response required within 0 – 6 months. |
| LOW risk: 1 - 4 | - Issue represents a minor control weakness, which is minimal but reportable impact on the ability of the process to achieve its objectives. Requires management attention and possible use of external resources. Requires action commensurate with the process objectives. Response required as soon as practicable. |
| Opportunity: 0 | - Issue represents a best practice improvement, which is not addressing an identified risk but looking to improve efficiencies and business practices. Requires review by management with a view to implement if considered practical and beneficial. |

Table 4: Risk Management Plan Example

Note: This is an event Risk Management Plan example ONLY, the list of hazards may be extensive depending on the activities within the project or event. Further information relating to hazards is available through Council’s Risk Officer 1800 065 993 or from the Work Safe publication - Advice for Managing Major Events Safely, please refer to www.worksafe.vic.gov.au.

| RISK MANAGEMENT PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Event |  | Village Market |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of event’s Risk Management Officer |  |  | Event Manager |  |  |  |  |  | Organisation |  | Events4us |  |  | Mobile |  |  |  | 0412 345 678 |  |
| People involved in compiling this plan |  |  | E Manager, A Helper, A Stall Holder, F Vendor |  |  |  |  |  |  |  |  |  |  | Today’s date |  |  |  | Fri 31 May 2013 |  |
| Event description |  | Stall holders selling home produce, entertainment and games for children |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location |  | Recreation reserve |  |  |  |  |  |  | Date of event | Sun 6 October 2026 |  |  |  | Time / duration |  |  |  | Start - 10:00am. Finish – 4:00pm |  |
| Expected crowd |  | 150 adults and children |  |  |  |  |  |  | Types of activities | Stalls selling produce, juggler, children’s games, wine tasting |  |  |  |  |  |  |  |  |  |
| 1 | 2 |  |  |  | 3 | 4 | 5 | 6 |  |  |  | 7 |  |  | 8 | 9 |  |  | 10 |
| Activity/ process/ contributor | Hazard / Risk |  |  |  | C conse-quence | L likely-hood | Risk rating | Control |  |  |  | Risk rating after control in place |  |  | Control implemented by | Control to be in place by |  |  | Control actually in place |
| Setting up stalls & marquees | Underground power. Pegs may contact power cables. Potential electrocution causing death. |  |  |  | 5 | 3 | High (15) | Accurately identify and locate underground power. Ensure clearance by 2.0m |  |  |  | Low |  |  | A Citizen | 2 weeks prior |  |  | 1 week prior |
|  | Guy ropes may cause tripping hazard. Potential for personal injury. |  |  |  | 3 | 5 | High (15) | Guy ropes highlighted with bright tape. Ropes limited to a span of 600mm from pole. |  |  |  | Low |  |  | Stall holder | On the day |  |  | On the day |
| Parking Weather/Environment | Vehicles have potential for serious injury or death to pedestrians. |  |  |  | 5 | 4 | High (20) | Documented Traffic Management Plan including designated parking area. Ensure vehicles maintain walking pace only with signage and trained traffic controllers. |  |  |  | Medium |  |  | Parking Coordinator | On the day |  |  | On the day |
|  | Extreme weather such as heat/wind/storm/flooding/bushfire/total fire ban days |  |  |  | 4 | 4 | Medium(12) | Weather will be monitored in the lead up to event and weather plan will be implemented if required *see attached |  |  |  | Medium |  |  | Event Manager | Prior event and on day |  |  | On the day |
|  | Snakes (wildlife) Snake bite injury/death. |  |  |  | 5 | 3 | High(15) | Grass maintenance, site inspection, first aid readiness. Snake Catcher |  |  |  | Meidum |  |  | Event Manager | Prior event and on day |  |  | On the day |
|  | Spiders / insects Bites/ stings allergic reactions. |  |  |  | 4 | 3 | Medium (12) | First aid officer Epi Pen |  |  |  | Low |  |  | Event Manager | On the day |  |  | On the Day |
|  | Sun exposure / UV Heat stress, sunburn. |  |  |  | 4 | 3 | Mediuom(12) | Shade, sunscreen, hydration stations. |  |  |  | Low |  |  | Event Manager | On the day |  |  | On the day |
|  | Drowning |  |  |  | 3 | 5 | High (15) | Barriers, signage, supervision, emergency response. |  |  |  | Medium |  |  | Event Manager | On the day |  |  | On the Day |
| People | Excessive alcohol has potential for illegal activity, violence causing injury or death. |  |  |  | 5 | 3 | High (15) | Liquor licence. Reduced serving hours. Also Refer Form Four. Security in attendance - details below. Police advised. |  |  |  | Medium |  |  | Event Manager | Prior event and on day |  |  | Licence 3 April Police advised 5 April |
|  | Manual handling Muscle strains/injury |  |  |  | 3 | 4 | Medium(12) | Safe lifting, trolleys, team lifting |  |  |  | Low |  |  | Event Manager | On the day |  |  | On the day |
|  | Dehydration (Loss of bodily fluids from illness, excessive temperature, exercise or not drinking enough water) |  |  |  | 4 | 3 | Medium (12) | Additional water stations will be hired from Strathbogie Shire Council for people to fill their water bottles at event. Water available at food stalls First aid available |  |  |  | Low |  |  | Event Manager | On the day |  |  | On the day |
|  | Lost children / vulnerable persons |  |  |  | 4 | 3 | Medium (12) | Lost person point, wristbands, announcements. |  |  |  | Low |  |  | Event Manager | On the day |  |  | On the day |
|  | Trips, slips and falls (general site) Injury from uneven or wet surfaces. |  |  |  | 4 | 4 | Medium(16) | Site inspection, cable management, spill cleanup, matting. |  |  |  | Low |  |  | Event Manager | Prior and on day |  |  | On the day |
|  | Medical Emergencies Anaphylaxis, Cardiac event, etc |  |  |  | 5 | 3 | High(15) | Clear area, first aid response, emergency access. EpiPens, trained first aid, emergency plan |  |  |  | Medium |  |  | First Aid | On the day |  |  | On the day |
|  | Lack of amenities resulting in illness/disease |  |  |  | 4 | 3 | Medium (12) | Location has adequate toilet and fresh water drinking facilities, amenities will be checked prior to event to ensure working order |  |  |  | Low |  |  | Event Manager | One week prior and on day |  |  | One week prior and on day |
| Food vendors | Potential for food poisoning resulting in illness or death. |  |  |  | 5 | 3 | Medium (9) | Compliance with Food Safety Program / Food Handling Permit |  |  |  | Low |  |  | Food Vendor | On the day |  |  | On the day |
|  | Electrocution from incorrectly used or faulty electrical items including exposure to water. |  |  |  | 5 | 3 | Medium (9) | Electrical leads to be inspected and tagged. Residual Current Devices to be in place. Power circuits fitted with appropriate rated fuses or circuit breaker. Use lead stands or insulated cable hangers to keep leads off ground. If not possible ensure suitable cover (matting) and no sharp stones etc. for pedestrian traffic. Timber protection for vehicular traffic. Unless especially designed, keep leads and tools clear of damp or wet conditions. Lead joins must be weather proof. |  |  |  | Medium |  |  | Food Vendor | On the day |  |  | On the day |
|  | Electrical leads on ground have potential for trip/fall injury. |  |  |  | 3 | 1 | High (15) | Leads clear of pedestrian traffic. |  |  |  | Low |  |  | Food Vendor | On the day |  |  | On the day |
|  |  |  |  |  |  |  |  | Leads covered with secure matting to remove trip hazard. Ensure no sharp stones etc. Note: matting not suitable for vehicular traffic. |  |  |  | Medium |  |  | Food Vendor | On the day |  |  | On the day |
| Other Hazards may include: (consider things that can cause harm or damage) |  Temporary structures – may need a Council permit  Gas appliances – must be Energy Safe Victoria compliant and have a Gas Safety, Self-checklist (www.esv.vic.gov.au) on site and available for inspection  Powered equipment including amusement rides and inflatable devices must have own Risk Assessment and Public Liability Insurance  Hazardous Substances & Dangerous Goods  Working at Height (ie >2m) – must have licence from Vicotiran Building Authority  Noise  Fireworks – must have WorkSafe permit  Contractors – must have own Risk Assessment or Job Safety Analysis and Public Liability Insurance  Entertainers – may need own Risk Management Plan depending on risk level and Public Liability Insurance  Code Red days – event should be postponed / cancelled to eliminate the risk Note: most of these hazards have the potential for serious injury or death and therefore likely to score an ‘Extreme’ risk. Controls must be put in place to reduce the risk Refer WorkSafe document Advice for Managing Major Events Safely available on www.worksafe.vic.gov.au for more information on hazards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If a security firm has been contracted, provide details below |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of company |  |  |  | A Security |  |  |  |  |  |  |  |  | Contact phone |  |  |  | 03 0000 0000 |  |  |
| Number of security personnel at event |  |  |  | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 4: Risk Management Plan template

| RISK MANAGEMENT PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of Risk Management Officer |  |  |  |  |  |  |  | Organisation |  |  |  | Mobile |  |  |  |  |
| People involved in compiling this plan |  |  |  |  |  |  |  |  |  |  |  | Today’s date |  |  |  |  |
| Project description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location |  |  |  |  |  |  |  | Date of event |  |  |  | Time / duration |  |  |  |  |
| Expected crowd |  |  |  |  |  |  |  | Types of activities |  |  |  |  |  |  |  |  |
| 1 | 2 |  |  | 3 | 4 | 5 | 6 |  |  |  | 7 |  | 8 | 9 |  | 10 |
| Activity/ process/ contributor | Hazard / Risk |  |  | C conse-quence | L likely-hood | Risk rating | Control |  |  |  | Risk rating after control in place |  | Control implemented by | Control to be in place by |  | Control actually in place |
| Other Hazards may include: (consider things that can cause harm or damage) |  Temporary structures – must have a Council permit  Gas appliances – must be Energy Safe Victoria compliant and have a Gas Safety, Self-checklist (www.esv.vic.gov.au) on site and available for inspection  Powered equipment including amusement rides – provider must have own Risk Management Plan if risk is greater than Low  Hazardous Substances & Dangerous Goods  Working at Height (ie >2m) – must be qualified and obtain Council Permit  Noise  Fireworks – must have WorkSafe permit  Contractors – must have own Risk Assessment or Job Safety Analysis  Entertainers – may need own Risk Management Plan depending on risk level  Code Red days – event should be postponed / cancelled to eliminate the risk Note: most of these hazards have the potential for serious injury or death and therefore likely to score an ‘Extreme’ risk. Controls must be put in place to reduce the risk Refer WorkSafe document Advice for Managing Major Events Safely available on www.worksafe.vic.gov.au for more information on hazards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| If a security firm has been contracted, provide details below |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of company |  |  |  |  |  |  |  |  |  |  | Contact phone |  |  |  |  |  |
| Number of security personnel at event if applicable |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |